## Sheet1
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Nethara G | 2026-06-30 | Project dependencies were not installed correctly | Sprint 1 | Nethara G | Environment | Installed required Python packages and virtual environment | 2026-06-30 | Closed | Resolved successfully
2 | Nethara G | 2026-07-01 | TruthfulQA dataset loading failed due to incorrect file path | Sprint 1 | Nethara G | Data | Corrected dataset path and verified loading | 2026-07-01 | Closed | Dataset loaded successfully
3 | Nethara G | 2026-07-02 | Embedding model download failed due to a network issue | Sprint 1 | Nethara G | Integration | Reconnected network and downloaded the model successfully | 2026-07-02 | Closed | Embeddings generated
4 | Nethara G | 2026-07-03 | ChromaDB connection issue while storing embeddings | Sprint 1 | Nethara G | Database | Reconfigured database path and recreated collection | 2026-07-03 | Closed | Vector database working
5 | Nethara G | 2026-07-04 | Question retrieval returned irrelevant results | Sprint 1 | Nethara G | Functional | Updated retrieval logic and verified retrieved answers | 2026-07-04 | Closed | Retrieval improved
6 | Nethara G | 2026-07-06 | FastAPI endpoint returned an import error | Sprint 1 | Nethara G | Backend | Fixed import statements and restarted server | 2026-07-06 | Closed | API working correctly
7 | Nethara G | 2026-07-07 | Streamlit frontend failed to connect to backend API | Sprint 1 | Nethara G | Integration | Corrected API URL and tested communication | 2026-07-07 | Closed | Frontend connected
8 | Nethara G | 2026-07-09 | Minor UI alignment issues in Streamlit interface | Sprint 1 | Nethara G | UI | Updated layout and improved interface | 2026-07-09 | Closed | Ready for Milestone 1 demo
9 | Nethara G | 2026-07-10 | Accuracy score was inconsistent | Sprint 2 | Nethara G | AI Evaluation | Improved prompt and scoring logic | 2026-07-10 | Closed | Accuracy improved
10 | Nethara G | 2026-07-11 | Hallucination detection gave incorrect result | Sprint 2 | Nethara G | AI Evaluation | Updated hallucination prompt | 2026-07-11 | Closed | Detection improved
11 | Nethara G | 2026-07-13 | Retrieved reference was not relevant | Sprint 2 | Nethara G | Retrieval | Improved retrieval logic | 2026-07-13 | Closed | Retrieval improved
12 | Nethara G | 2026-07-15 | Judge Agent UI alignment issue | Sprint 2 | Nethara G | UI | Updated dashboard layout | 2026-07-15 | Closed | Dashboard improved
13 | Nethara G | 2026-07-17 | Overall score displayed incorrectly | Sprint 2 | Nethara G | Functional | Corrected score calculation | 2026-07-17 | Closed | Overall score fixed
14 | Nethara G | 2026-07-19 | Evaluation response display issue | Sprint 2 | Nethara G | Backend | Fixed response display logic | 2026-07-19 | Closed | Evaluation displayed correctly
15 | Nethara G | 2026-07-21 | Batch CSV evaluation required correction | Sprint 3 | Nethara G | Functional | Corrected batch processing logic and retested | 2026-07-22 | Closed | Batch evaluation working
16 | Nethara G | 2026-07-23 | Dashboard chart values required correction | Sprint 3 | Nethara G | UI | Corrected chart data mapping | 2026-07-24 | Closed | Charts displayed correctly
17 | Nethara G | 2026-07-25 | PDF report formatting required correction | Sprint 3 | Nethara G | Report | Updated PDF formatting and layout | 2026-07-26 | Closed | PDF generated correctly
18 | Nethara G | 2026-07-28 | Batch results required dashboard integration correction | Sprint 3 | Nethara G | Integration | Updated batch result handling | 2026-07-29 | Closed | Results displayed correctly
19 | Nethara G | 2026-07-30 | Milestone 3 features required final testing | Sprint 3 | Nethara G | Functional | Tested dashboard, batch evaluation and PDF export | 2026-07-31 | Closed | Milestone 3 completed
20 | Nethara G | 2026-08-01 | End-to-end workflow required validation | Sprint 4 | Nethara G | Functional | Tested complete workflow from input to report | 2026-08-02 | Closed | Workflow verified
21 | Nethara G | 2026-08-03 | Invalid input handling required improvement | Sprint 4 | Nethara G | Validation | Added and tested input validation | 2026-08-04 | Closed | Invalid inputs handled
22 | Nethara G | 2026-08-05 | Technical documentation formatting required corrections | Sprint 4 | Nethara G | Documentation | Corrected diagrams, page numbering and formatting | 2026-08-06 | Closed | Documentation completed
23 | Nethara G | 2026-08-07 | Project report formatting required final review | Sprint 4 | Nethara G | Documentation | Finalized report formatting and screenshots | 2026-08-08 | Closed | Project report completed
24 | Nethara G | 2026-08-09 | Final demonstration workflow required organization | Sprint 4 | Nethara G | Demonstration | Organized single, batch, dashboard and report demonstration | 2026-08-10 | Closed | Demo ready
25 | Nethara G | 2026-08-11 | Final project verification required | Sprint 4 | Nethara G | Functional | Performed final system verification and milestone review | 2026-08-11 | Closed | Milestone 4 completed