## Sheet1
Sprint # | Sprint Start Date | Sprint End Date | Team Member Name | Start Doing | Stop Doing | Continue Doing | Action Taken
Sprint 1 | 2026-06-30 | 2026-07-09 | Nethara G | Set up project structure, GitHub repository | Working without proper project structure | Learning project architecture | Created repository and organized folders
Sprint 1 | 2026-06-30 | 2026-07-09 | Nethara G | Implement dataset loading and document chunking | Manual document handling | Improve preprocessing | Integrated dataset loading and document chunking
Sprint 1 | 2026-06-30 | 2026-07-09 | Nethara G | Generate embeddings using SentenceTransformer | Using raw text for search | Optimize embeddings | Generated embeddings and stored them in ChromaDB
Sprint 1 | 2026-06-30 | 2026-07-09 | Nethara G | Implement retrieval module | Keyword-based retrieval | Improve semantic search | Implemented retrieval module and connected it with ChromaDB
Sprint 1 | 2026-06-30 | 2026-07-09 | Nethara G | Develop FastAPI backend | Testing APIs manually | API optimization | Created evaluation API endpoint
Sprint 1 | 2026-06-30 | 2026-07-09 | Nethara G | Connect frontend with backend | Static frontend pages | Improve UI and integration | Integrated frontend with FastAPI
Sprint 1 | 2026-06-30 | 2026-07-09 | Nethara G | Test complete system and fix bugs | Ignoring edge cases | Performance improvement | Fixed bugs and prepared project demo
Sprint 2 | 2026-07-10 | 2026-07-19 | Nethara G | Develop Accuracy Agent | Manual response checking | Improve evaluation quality | Implemented Accuracy Agent
Sprint 2 | 2026-07-10 | 2026-07-19 | Nethara G | Develop Relevance Agent | Simple keyword matching | Improve semantic evaluation | Implemented Relevance Agent
Sprint 2 | 2026-07-10 | 2026-07-19 | Nethara G | Develop Hallucination Agent | Manual hallucination detection | Improve AI validation | Implemented Hallucination Agent
Sprint 2 | 2026-07-10 | 2026-07-19 | Nethara G | Improve evaluation dashboard | Basic UI layout | Enhance user interface | Created evaluation dashboard
Sprint 2 | 2026-07-10 | 2026-07-19 | Nethara G | Integrate Judge Agents | Separate evaluation modules | Improve integration | Integrated all Judge Agents
Sprint 2 | 2026-07-10 | 2026-07-19 | Nethara G | Perform complete testing | Partial testing | Validate system performance | Completed Milestone 2 testing
Sprint 3 | 2026-07-20 | 2026-07-31 | Nethara G | Implemented batch CSV evaluation | Batch processing required debugging | Learned batch evaluation workflow | Successfully evaluated multiple AI responses using CSV
Sprint 3 | 2026-07-20 | 2026-07-31 | Nethara G | Developed evaluation scoring dashboard | Dashboard layout required refinement | Learned to present evaluation metrics clearly | Added evaluation scores and visualizations
Sprint 3 | 2026-07-20 | 2026-07-31 | Nethara G | Implemented PDF evaluation report generation | Report formatting required corrections | Learned structured report generation | Generated structured PDF evaluation reports
Sprint 3 | 2026-07-20 | 2026-07-31 | Nethara G | Integrated batch results with dashboard | Some results needed verification | Learned dashboard integration | Completed batch evaluation dashboard
Sprint 3 | 2026-07-20 | 2026-07-31 | Nethara G | Tested Milestone 3 features | Minor integration issues were found | Learned end-to-end feature validation | Completed Milestone 3 implementation
Sprint 4 | 2026-08-01 | 2026-08-11 | Nethara G | Performed end-to-end testing | Minor integration issues required verification | Learned complete system validation | Verified single and batch workflows
Sprint 4 | 2026-08-01 | 2026-08-11 | Nethara G | Validated RAG retrieval and agent scoring | Some results required consistency checking | Learned evaluation validation techniques | Verified RAG and agent evaluation outputs
Sprint 4 | 2026-08-01 | 2026-08-11 | Nethara G | Prepared technical documentation | Formatting required final corrections | Learned technical documentation practices | Completed technical documentation
Sprint 4 | 2026-08-01 | 2026-08-11 | Nethara G | Prepared project report | Final formatting required review | Learned formal project reporting | Completed project report
Sprint 4 | 2026-08-01 | 2026-08-11 | Nethara G | Prepared final project demonstration | Demo flow required organization | Learned how to present the complete system | Prepared project for final demonstration