## Sheet1
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Nethara G | 2026-06-30 | Project dependencies were not installed correctly | Sprint 1 | Nethara G | Environment | Installed required Python packages and virtual environment | 2026-06-30 | Closed | Resolved successfully
2 | Nethara G | 2026-07-01 | TruthfulQA dataset loading failed due to incorrect file path | Sprint 1 | Nethara G | Data | Corrected dataset path and verified loading | 2026-07-01 | Closed | Dataset loaded successfully
3 | Nethara G | 2026-07-02 | Embedding model download failed due to a network issue | Sprint 1 | Nethara G | Integration | Reconnected network and downloaded the model successfully | 2026-07-02 | Closed | Embeddings generated
4 | Nethara G | 2026-07-03 | ChromaDB connection issue while storing embeddings | Sprint 1 | Nethara G | Database | Reconfigured database path and recreated collection | 2026-07-03 | Closed | Vector database working
5 | Nethara G | 2026-07-04 | Question retrieval returned irrelevant results | Sprint 1 | Nethara G | Functional | Updated retrieval logic and verified retrieved answers | 2026-07-04 | Closed | Retrieval improved
6 | Nethara G | 2026-07-06 | FastAPI endpoint returned an import error | Sprint 1 | Nethara G | Backend | Fixed import statements and restarted server | 2026-07-06 | Closed | API working correctly
7 | Nethara G | 2026-07-07 | Streamlit frontend failed to connect to backend API | Sprint 1 | Nethara G | Integration | Corrected API URL and tested communication | 2026-07-07 | Closed | Frontend connected
8 | Nethara G | 2026-07-09 | Minor UI alignment issues in Streamlit interface | Sprint 1 | Nethara G | UI | Updated layout and improved interface | 2026-07-09 | Closed | Ready for Milestone 1 demo