## Sheet1
Sprint # | Sprint Start Date | Sprint End Date | Team Member Name | Start Doing | Stop Doing | Continue Doing | Action Taken
Sprint 1 | 2026-06-30 | 2026-07-09 | Nethara G | Set up project structure, GitHub repository | Working without proper project structure | Learning project architecture | Created repository and organized folders
Sprint 1 | 2026-06-30 | 2026-07-09 | Nethara G | Implement dataset loading and document chunking | Manual document handling | Improve preprocessing | Integrated dataset loading and document chunking
Sprint 1 | 2026-06-30 | 2026-07-09 | Nethara G | Generate embeddings using SentenceTransformer | Using raw text for search | Optimize embeddings | Generated embeddings and stored them in ChromaDB
Sprint 1 | 2026-06-30 | 2026-07-09 | Nethara G | Implement retrieval module | Keyword-based retrieval | Improve semantic search | Implemented retrieval module and connected it with ChromaDB
Sprint 1 | 2026-06-30 | 2026-07-09 | Nethara G | Develop FastAPI backend | Testing APIs manually | API optimization | Created evaluation API endpoint
Sprint 1 | 2026-06-30 | 2026-07-09 | Nethara G | Connect frontend with backend | Static frontend pages | Improve UI and integration | Integrated frontend with FastAPI
Sprint 1 | 2026-06-30 | 2026-07-09 | Nethara G | Test complete system and fix bugs | Ignoring edge cases | Performance improvement | Fixed bugs and prepared project demo